## WBS2
ir
Work Breakdown structure
Project Title
Project Detail
|  |  |  | Client | [6 empty] | PM |  | Office
|  |  |  | Project No. |  |  | Type of Job |  | Sector |  | SPM |  | Region
|  |  |  | Type of Client |  |  | Estimated Project Cost |  | Fee Type | (Lumpsum/Item Rate) | Start Date |  | End Date
|  |  |  | Estimated Project Cost |  |  |  |  | Period
WORK BREAKDOWN STRUCTURE | [11 empty] | Resource (Hours budgeted)
WBS Levels | [6 empty] | 2015-01-01 | 2015-02-02 | 2015-03-06 | 2015-04-07 | 2015-05-09 | 2015-06-10 | 2015-07-12 | 2015-08-13 | 2015-09-14 | 2015-10-16 | 2015-11-17 | 2015-12-19 | Total | Total | ODCs | Total
Level 1 | Level 2 | Level 3 |  | Role | Name | Cost Rate | [12 empty] | Hours | Time Cost |  | Cost
| 1.4 |  | Preparation of Draft Detailed Design report | Project Manager | Manasi Bapat | [13 empty] | 0 | 0 |  | 0
Topographical survey
|  | 1.4.1 | Detailed Design | Project Manager | Manasi Bapat |  |  | 16 | 16 | [9 empty] | 32 | 0 |  | 0
|  | 1.4.2 | Preparation of LS and plans | Project Manager | Manasi Bapat |  |  | 16 | 16 | [9 empty] | 32 | 0 |  | 0
|  | 1.4.2 | Preparation of LS and plans | CAD | Francis Rumao |  |  | 40 | 40 | [9 empty] | 80
|  | 1.4.3 | Preparation of BOQ | Project Manager | Manasi Bapat |  |  |  | 16 | [9 empty] | 16 | 0 |  | 0
|  | 1.4.4 | Preparation of Draft DDR | Project Manager | Manasi Bapat |  |  | 24 | 16 | [9 empty] | 40 | 0 |  | 0
|  | 1.4.4 | Preparation of Draft DDR | Senior Project Manager | Mandar Pimputkar |  |  |  | 40 | [9 empty] | 40
|  | 1.4.4 | Preparation of Draft DDR | Cliet Service Manager | Vidyadhar Vengurlekar |  |  |  | 40 | [9 empty] | 40
|  | 1.4.4 | Preparation of Draft DDR | CAD | Francis Rumao |  |  |  | 80 | [9 empty] | 80
|  | 1.4.5 | Submission of Draft DDR | Project Manager | Manasi Bapat |  |  |  | 8 | [9 empty] | 8 | 0 |  | 0
| 1.5 |  | Comments and Reviews from client | [15 empty] | 0 | 0 |  | 0
|  | 1.5.1 | Client Presentation | Project Manager | Manasi Bapat |  |  |  | 24 | [9 empty] | 24 | 0 |  | 0
|  | ` | Client Presentation | Senior Project Manager | Mandar Pimputkar |  |  |  | 16 | [9 empty] | 16
|  | 1.5.1 | Client Presentation | Cliet Service Manager | Vidyadhar Vengurlekar |  |  |  | 16 | [9 empty] | 16
|  | 1.5.2 | Compliance of client comments | Project Manager | Manasi Bapat |  |  |  | 16 | [9 empty] | 16 | 0 |  | 0
|  | 1.5.3 | Submission of Final DDR | Project Manager | Manasi Bapat |  |  |  | 8 | [9 empty] | 8 | 0 |  | 0
| 1.6 |  | Preparation of Tender Documents | [15 empty] | 0 | 0 |  | 0
|  | 1.6.1 | Prepration of Draft Tender | Project Manager | Manasi Bapat |  |  |  | 40 | [9 empty] | 40 | 0 |  | 0
|  | 1.6.1 | Prepration of Draft Tender | Senior Project Manager | Mandar Pimputkar |  |  |  | 16 | [9 empty] | 16
|  | 1.6.1 | Prepration of Draft Tender | Cliet Service Manager | Vidyadhar Vengurlekar |  |  |  | 16 | [9 empty] | 16
|  | 1.6.2 | Submission of Draft Tender | Project Manager | Manasi Bapat |  |  |  | 8 | [9 empty] | 8 | 0 |  | 0
[19 empty] | 0 | 0 |  | 0
[6 empty] | Total Hours: | 0 | 96 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 0 | 0 | 0
[6 empty] | Total Cost: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
[20 empty] | (Check: OK) |  | (Check: OK)
Note on C24: Add Level 1 activities in this column
Note on D24: Add Level 2 activities in this column
Note on E24: Add Level 3 activities in this column