## Monthly PjM Report
Process for Completion
Actual Costs / Costs to Complete
1. Actual Costs reported in system 2. Costs accrued but not in system to date must be included in total EAC 3. Take account of provisions to compare EBBIT
Monthly Progress Review | [8 empty] | Earned Value data from EVA Spreadsheet
Project Title | [8 empty] | EVA will start mid-2008 for India and will be carried out for:- - Fixed Fee (Lump Sum) and Fee Capped Projects - Where project fee > InR 160,000 - and project duration > 3 months EVA is not required for seconded staff jobs
Project Detail |  |  | Project Number |  | Review No |  | Review Month
|  |  | Office |  | Region |  | PM
Client |  |  | Type of Job |  | Sector |  | SPM
Fees |  |  | Budget Costs |  |  | Contract Type
Net | Service Tax | Total | ODCs | Staff | Sub Total | Lumpsum | T & E | %
3286500 | 12.36% | 3750000 | #REF! |  |  | Yes
Actual Costs (AC) - InR in IMS |  |  | Any Accruals not in system | Costs To Complete (CTC) |  |  | Total EAC Estimate At Completion | Gross Profit %
ODCs | Staff | Subtotal |  | ODCs | Staff | Subtotal
#REF! |  |  | 0 |  |  | 0 | 0
|  |  | Revenue/Fee | Cost | Profit(%) | SCHEDULE PERFORMANCE
Original Budget |  |  | - |  |  | Date of issue of WO/LOI: |  | 04.03.2014
Current Budget in IMS |  |  | 0 |  |  | Completion Date as per contract: |  | 4.15.2014
% Complete on costs: | [5 empty] | Completion Date as per extension: |  | 31.12.2015
% Complete on EV (PPC): | [5 empty] | Expected Completion Date: |  | 31.12.2015
SPI:
MANPOWER PLANNED FOR REMAINING WORKS
Work Assignment |  | Assignee | Effort in Mandays |  |  |  | Comments
|  |  | Planned | Consumed | Balance | Next Month's Planning
Topographical Survey |  | Lavisha Surveyor | 30 | 30 | 0 | 0 | Survey is done by Surveyor by Oct 2014 |  | Milestones | 0
Geotechnical Survey |  | SKW Surveyor | 60 | 50 | 10 | 0 | Survey is done by Surveyor by Apr 2015 |  | Add all the milestones as per contract
Hydraulic Modelling |  | MB, MP, VV | 10 | 20 | -10 | 0 | Hydrualic Modelling is completed and L-sections are submitted to client on Feb 2015 |  | Add dates of submittals
Draft DDR |  | MB, MP, VV, FR | 30 | 90 | -60 | 0 | Draft DDR is submitted on June 2014 |  | Add planned payment details
Final DDR |  | MB, MP, VV, FR | 30 | 30 | 0 | 15 | Final DDR is submitted on Feb 2015. |  | Add payment details as project progress on monthly basis
Draft Tender docs |  | MB, MP, VV, FR | 15 | 2 | 13 | 0 | Draft tender documents are submitted on Feb 2015
Final Tender docs |  | MB, MP, VV | 15 | 0 | 15 | 0
Tender Evaluation and Award of work |  | MB, MP, VV | 15 | 0 | 15 | 0
|  |  | 190 | 222 | -32 | 15
PROGRESS REVIEW FOR DELIVERABLES
Miletsone | Due date as per contract | Due date as planned | Achieved Date | Payment due Rs. | Invoice date | Payment Received Date | Comments / Issues on Milestone / payment
Part A | [8 empty] | Variation
Advance payment |  |  |  | 300110 | 2014-05-01 |  | Payment is not received against invoice. |  | Reason why current projected schedule, ODCs differs from original budget, or from recent re-forecast
Inception Report | 20.03.2014 | - | 2014-05-01 | 150055 | 2014-05-01 | - | Payment is not received against invoice.
Detailed Project Report | 30.05.2014 | 2015-01-01 | 2015-02-15 | 750275 | 2015-02-15 | - | Payment is not received against invoice.
Submission of estimate, bill of quantities, specifications, drawings | 30.06.2014 | 2015-02-01 | 2015-02-15 | 600220 | 2015-02-15 | - | Payment is not received against invoice. |  | Contract Variation
Draft Tender Doc | 30.06.2014 | 2015-02-01 | 2015-02-15 | 900330 |  | - | MCGM to finalize packaging and technology options |  | Summarise change and detail this month's new scope changes Note any status change (provisional, submitted to Client, Approved). Budget Fee cannot be revised until change approved by Client.
Tender Evaluation Report | 15.07.2014 | 2015-02-01 | - | 150055 | - | - | MCGM to finalize packaging and technology options
Completion of construction work | 1.08.2014 | Mid Mar 15 | - | 150055 | - | -
Add more milestones if required | [8 empty] | Programme/Schedule
Comment on any gains or slippage since last month. Explain and quantify any changes to overall expected completion date Has an extension of time been sought or approved?
Change Orders Summary (compiled from Change Register)
Cont. Total | Cost | Fee | Summary Details of Changes this month
Proposed | NIL | NIL | NIL
Submitted | NIL | NIL | NIL
Approved | NIL | NIL | NIL
Programme / Schedule ( Delays Holds Deviations this month):
1. Delays caused due to lack of permission for geotech in monsoons | [8 empty] | Issies, Risks, Early Warnings
2. Discussions with various stakeholderss within or outside client organization | [8 empty] | If the contract allows imposition of penalties or liquidated damages, state rate of penalty and state maximum limit (Rupees or %) Highlight any issues that have arisen this month or risks that could have an impact on Project Finance, Schedule, Resources or Quality in the future. Provide update on previously noted risks/opportunities The list of items to consider is a only a suggestion based on the most commonly arising ones – consider any other issues that should be noted for this project.
Issues, Risks, Early Warnings
Financial Penalties specified in the Contract: %age ( ) Max. %age ( ) |  |  |  | Please mention as applicable
Client Feedback/Rltnshp Inflation |  |  | Resources Oppts |  | QA HSE | Contract Insurance/Guarantees
1. Payment has not been received from MCGM for two which have been raised invoices
Actions from last month
Report on actions from previous months - comment on outstanding actions
Actions and Priorities
Set realistic dates taking account of priorities (H - Immediately, M - within one week, L - within one month)
Actions from last month |  |  |  | Date | Comments
1. Meetings with MCGM for finalization of techniques of execution
2. Site visits with MCGM for slum sanitation schemes
3. Chasing to payment of invoices raised
Actions and Priorities for this month: | [6 empty] | Date | H / M / L
1. Cost comparison to be submitted to MCGM for various techniques | [6 empty] | 2015-08-10 | H
2. Re-doing the final detailed project report and finalization of tenders | [6 empty] | 2015-09-11 | H
3. Chasing to payment of invoices raised | [7 empty] | H